## Team
Initials | First | Last | Email | GitHub Username
AD | Akash | Desai | adesai4@stevens.edu | amdesai97
PK | Priyanka | Koul | pkoul1@stevens.edu | pkoul1stevens
SB | Shashidhar | Naidu Boya | sboya1@stevens.edu | shashidharnaiduboya
SK | Shubham | Kulkarni | skulkarn1@stevens.edu | Shubham-andy7
|  |  |  | GitHub Repository | https://github.com/Shubham-andy7/CS555_Group_Project_Team7_Main

## Backlog
Sprint No | User Story ID | User Story Name | Owner | Status
1 | US_01 | Dates before current date | SB | completed
1 | US_02 | Birth before marriage | SB | completed
1 | US_03 | Birth before death | SK | completed
1 | US_04 | Marriage before divorce | SK | completed
1 | US_05 | Marriage before death | AD | completed
1 | US_06 | Divorce before death | AD | completed
1 | US_07 | Less then 150 years old | PK | completed
1 | US_08 | Birth before marriage of parents | PK | completed
2 | US_09 | Birth before death of parents | SB | completed
2 | US_10 | Marriage after 14 | SB | completed
2 | US_11 | No bigamy | SK | completed
2 | US_12 | Parents not too old | SK | completed
2 | US_13 | Siblings spacing | AD | completed
2 | US_14 | Multiple births <= 5 | AD | completed
2 | US_15 | Fewer than 15 siblings | PK | completed
2 | US_16 | Male last names | PK | completed
3 | US_17 | No marriages to descendants | SB | completed
3 | US_18 | Siblings should not marry | SB | completed
3 | US_19 | First cousins should not marry | SK | completed
3 | US_20 | Aunts and uncles | SK | completed
3 | US_21 | Correct gender for role | AD | completed
3 | US_22 | Unique IDs | AD | completed
3 | US_23 | Unique name and birth date | PK | completed
3 | US_24 | Unique families by spouses | PK | completed
4 | US_25 | Unique first names in families | SK | completed
4 | US_26 | Corresponding entries | SK | completed
4 | US_27 | Include individual ages | SB | completed
4 | US_28 | Order siblings by age | SB | completed
4 | US_29 | List deceased | AD | completed
4 | US_30 | List living married | AD | completed
4 | US_31 | List living single | PK | completed
4 | US_32 | List multiple births | PK | completed

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2023-06-02 | 32 | 0 | 0 |  | 0
Sprint 1 | 2023-06-15 | 24 | 8 | 330 | 165 | 160
Sprint 2 | 2023-06-29 | 16 | 8 | 589 | 145 | 120
Sprint 3 | 2023-07-10 | 8 | 8 | 820 | 220 | 182
Sprint 4 | 2023-07-26 | 0 | 8 | 1024 | 440 | 320
= # team members * 4 sprints *
2 stories per sprint
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
lines of code per hour is calcuated by Excel
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2023-06-02 | 32 |  | 0
2023-06-15 | 32 | 8 | 330 | 165 | 160
2023-06-29 | 24 | 8 | 589 | 145 | 120
2023-07-13 | 16 | 8 | 820 | 220 | 182
2023-07-27 | 8 | 8 | 1024 | 440 | 320
2023-08-10 | 0 | 0

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | SB | implemented | 5 | 30 |  | 20 | 2023-06-14
US02 | Birth before marriage | SB | implemented | 5 | 40 |  | 15 | 2023-06-14
US03 | Birth before death | SK | implemented | 5 | 20 |  | 15 | 2023-06-12
US04 | Marriage before divorce | SK | implemented | 5 | 20 |  | 15 | 2023-06-12
US05 | Marriage before death | AD | implemented | 5 | 40 |  | 30 | 2023-06-12
US06 | Divorce before death | AD | implemented | 5 | 40 |  | 20 | 2023-06-12
US07 | Less then 150 years old | PK | implemented | 5 | 30 |  | 30 | 2023-06-13
US08 | Birth before death of parents | PK | implemented | 5 | 30 |  | 20 | 2023-06-13
[9 empty] | Keep Doing: | Continue following the same approach for the sprint implementation, reviews and meeting plans.
[9 empty] | Avoid | Avoid leaving the discussions for last minutes

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US_09 | Birth before marriage of parents | SB | implemented | 35 | 40 | 40 | 20 | 2023-07-13
US_10 | Marriage after 14 | SB | implemented | 5 | 40 | 4 | 25 | 2023-07-13
US_11 | No bigamy | SK | implemented | 20 | 30 | 38 | 15 | 2023-07-11
US_12 | Parents not too old | SK | implemented | 20 | 30 | 45 | 20 | 2023-07-11
US_13 | Siblings spacing | AD | implemented | 15 | 30 | 29 | 15 | 2023-07-12
US_14 | Multiple births <= 5 | AD | implemented | 15 | 40 | 17 | 20 | 2023-07-12
US_15 | Fewer than 15 siblings | PK | implemented | 20 | 40 | 20 | 15 | 2023-07-11
US_16 | Male last names | PK | implemented | 20 | 30 | 35 | 15 | 2023-07-11
[9 empty] | Keep Doing: | getting each team member equally involved in the task. Taking everyone's feedback by doing informal peer-reviews.
[9 empty] | Avoid | Irrelevant discussions during the meetings.
Communication gaps

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US_17 | No marriages to descendants | SB | implemented | 30 | 30 | 40 | 20 | 2023-07-27
US_18 | Siblings should not marry | SB | implemented | 5 | 30 | 4 | 20 | 2023-07-27
US_19 | First cousins should not marry | SK | implemented | 20 | 25 | 38 | 15 | 2023-07-26
US_20 | Aunts and uncles | SK | implemented | 20 | 25 | 45 | 20 | 2023-07-26
US_21 | Correct gender for role | AD | implemented | 20 | 20 | 29 | 20 | 2023-07-26
US_22 | Unique IDs | AD | implemented | 25 | 20 | 17 | 15 | 2023-07-26
US_23 | Unique name and birth date | PK | implemented | 15 | 25 | 20 | 15 | 2023-07-25
US_24 | Unique families by spouses | PK | implemented | 15 | 25 | 35 | 20 | 2023-07-25
[9 empty] | Keep Doing: | peer-review of the User Story developed by each team member and providing feedbacks to improve the script.
[9 empty] | Avoid: | leaving discussions for the last minutes

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US25 | Unique first names in families | SK | Assigned | 35 | 20 | 40 | 20 | 2023-08-09
US26 | Corresponding entries | SK | Assigned | 5 | 25 | 4 | 15 | 2023-08-09
US27 | Include individual ages | SB | Assigned | 20 | 15 | 38 | 15 | 2023-08-08
US28 | Order siblings by age | SB | Assigned | 20 | 13 | 45 | 10 | 2023-08-08
US29 | List deceased | AD | Assigned | 15 | 20 | 29 | 10 | 2023-08-07
US30 | List living married | AD | Assigned | 15 | 25 | 17 | 15 | 2023-08-07
US31 | List living single | PK | Assigned | 20 | 25 | 20 | 20 | 2023-08-08
US32 | List multiple births | PK | Assigned | 20 | 15 | 35 | 10 | 2023-08-08
20
[9 empty] | Keep Doing: | following same way of communication, equal involvemen and contribution, peer-review and feedbacks.
[9 empty] | Avoid: | implementing the Sprints at last day.

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before death of parents | Child should be born before the death of the mother and before 9 months after the death of the father
US09 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file